## Sheet1
Task ID	Type	Task Name	Sprint	Estimated Time	Logged Time	Start Date	End Date	Status	Logged Date
HUR000006	Task	converting HSSE report CRUD methods section to cakephp 3.8	SEPT 25	16	8	03 October, 2025	06 October, 2025	Done	Friday 3rd of October 2025 04:25 PM
HUR000006	Task	converting HSSE report CRUD methods section to cakephp 3.8	SEPT 25		8	03 October, 2025	06 October, 2025	Done	Monday 6th of October 2025 04:25 PM
HUR000006	Task	converting HSSE report CRUD methods section to cakephp 3.8	SEPT 25		8	03 October, 2025	06 October, 2025	Done	Wednesday 8th of October 2025 04:25 PM
HUR000006	Task	converting HSSE report CRUD methods section to cakephp 3.8	SEPT 25		8	03 October, 2025	06 October, 2025	Done	Tuesday 7th of October 2025 04:25 PM
HUR000007	Task	converting HSSE report CRUD methods section to cakephp 3.8	SEPT 25	10	9	09 October, 2025	10 October, 2025	Done	Thursday 9th of October 2025 04:38 PM
HUR000008	Task	HSSE Reports in Incident Add, edit, delete active and inactive actions	SEPT 25	16	9	10 October, 2025	13 October, 2025	Done	Friday 10th of October 2025 05:02 PM
HUR000008	Task	HSSE Reports in Incident Add, edit, delete active and inactive actions	SEPT 25		8	10 October, 2025	13 October, 2025	Done	Monday 13th of October 2025 05:02 PM
HUR000009	Task	HSSE Reports in Incident Add, edit, delete active and inactive actions	SEPT 25	16	8	14 October, 2025	16 October, 2025	Done	Tuesday 14th of October 2025 03:56 PM
HUR000009	Task	HSSE Reports in Incident Add, edit, delete active and inactive actions	SEPT 25		8	14 October, 2025	16 October, 2025	Done	Wednesday 15th of October 2025 03:54 PM
HUR000009	Task	HSSE Reports in Incident Add, edit, delete active and inactive actions	SEPT 25		8	14 October, 2025	16 October, 2025	Done	Thursday 16th of October 2025 03:54 PM
HUR000010	Task	setting up New Project in Cakephp5	SEPT 25	25	8	16 October, 2025	20 October, 2025	Done	Wednesday 22nd of October 2025 03:59 PM
HUR000010	Task	setting up New Project in Cakephp5	SEPT 25		8	16 October, 2025	20 October, 2025	Done	Friday 17th of October 2025 03:59 PM
HUR000011	Task	login section module	SEPT 25	38	8	23 October, 2025	30 October, 2025	Done	Thursday 23rd of October 2025 07:49 PM
HUR000011	Task	login section module	SEPT 25		9	23 October, 2025	30 October, 2025	Done	Friday 24th of October 2025 07:50 PM
HUR000011	Task	login section module	SEPT 25		9	23 October, 2025	30 October, 2025	Done	Monday 27th of October 2025 07:49 PM
HUR000012	Task	HSSE Reports listing	SEPT 25	38	9	28 October, 2025	03 November, 2025	Done	Tuesday 28th of October 2025 12:30 PM
HUR000012	Task	HSSE Reports listing	SEPT 25		9	28 October, 2025	03 November, 2025	Done	Wednesday 29th of October 2025 12:30 PM
HUR000012	Task	HSSE Reports listing	SEPT 25		9	28 October, 2025	03 November, 2025	Done	Thursday 30th of October 2025 12:30 PM
HUR000012	Task	HSSE Reports listing	SEPT 25		9	28 October, 2025	03 November, 2025	Done	Friday 31st of October 2025 12:30 PM